## Risk Register
Risk ID | Risk Description | Affected Asset | Category | Likelihood | Impact | Risk Score | Priority | Mitigation Strategy | Target Date
RISK-001 | Unauthorized Access to Customer Database | Customer Database | Access Management | Almost Certain | Extreme/Catastrophic | 10 | Critical | Implement MFA and quarterly access reviews | July 22, 2026
RISK-002 | Unpatched Systems Leading to Exploitation | Core Banking Server | Technical Vulnerability Management | Likely | Major | 6.4 | Medium | Implement automated patch management and enforce 72 hour critical patch window | September 22, 2026
RISK-003 | Phishing Attack on Employees | Employee Laptops | Access Management | Almost Certain | Major | 8 | High | Launch phishing simulations and increase security awareness training frequency | August 1, 2026
RISK-004 | Data Breach via Third Party Vendor | Customer Database | Third-Party Management | Credible | Extreme/Catastrophic | 6 | Medium | Formalize vendor security assessment process and include security requirements in all contracts | September 1, 2026
RISK-005 | Ransomware Attack on Core Banking Server | Core Banking Server | Technical Vulnerability Management | Credible | Extreme/Catastrophic | 6 | Medium | Deploy SIEM and verify backup recovery capability quarterly | September 22, 2026
RISK-006 | Insider Threat Data Exfiltration | Customer Database | Sensitive Data Management | Unlikely | Extreme/Catastrophic | 4 | Medium | Implement user behavior monitoring and enforce least privilege access | October 1, 2026
RISK-007 | DDoS Attack on ATM Network | ATM Network | Technical Vulnerability Management | Credible | Major | 4.8 | Medium | Deploy DDoS mitigation service and implement network traffic monitoring | September 1, 2026
RISK-008 | Misconfigured AWS S3 Bucket Exposing Customer Data | Cloud Storage | Sensitive Data Management | Credible | Extreme/Catastrophic | 6 | Medium | Run AWS Config rules to detect public buckets and implement automated policy compliance checks | July 22, 2026
RISK-009 | VPN Credential Compromise Leading to Network Breach | VPN Gateway | Access Management | Likely | Extreme/Catastrophic | 8 | High | Enforce MFA on VPN gateway and monitor access logs for anomalous patterns | August 1, 2026
RISK-010 | Physical Theft of Employee Laptop | Employee Laptops | Sensitive Data Management | Unlikely | Moderate | 2.4 | Low | Deploy full disk encryption and enable remote wipe capability on all laptops | August 22, 2026

## Control Maturity Scorecard
Control ID | Control Name | NIST Function | Current Maturity | Desired Maturity | Status
ID.AM-1 | Asset Management Policy | Identify | Performed | Optimizing | Pass
ID.RA-1 | Risk Assessment Procedure | Identify | Performed | Optimizing | Pass
ID.SC-1 | Third Party Risk Management | Identify | Documented | Optimizing | Pass
PR.AC-1 | Access Control Policy | Protect | Managed | Optimizing | Pass
PR.AC-2 | Physical Security Controls | Protect | Managed | Optimizing | Pass
PR.AC-7 | Multi-Factor Authentication | Protect | Not Performed | Optimizing | Fail
PR.AT-1 | Security Awareness Training | Protect | Documented | Optimizing | Pass
PR.DS-1 | Data Encryption Standard | Protect | Performed | Optimizing | Pass
PR.IP-1 | Patch Management Procedure | Protect | Documented | Optimizing | Pass
DE.AE-1 | Anomaly Detection Policy | Detect | Not Performed | Optimizing | Fail
DE.CM-1 | SIEM Monitoring | Detect | Not Performed | Optimizing | Fail
DE.CM-3 | Log Review Procedure | Detect | Performed | Optimizing | Pass
DE.CM-4 | Intrusion Detection System | Detect | Not Performed | Optimizing | Fail
RS.AN-1 | Root Cause Analysis | Respond | Performed | Optimizing | Pass
RS.CO-1 | Incident Communication Plan | Respond | Performed | Optimizing | Pass
RS.MI-1 | Incident Containment Procedure | Respond | Documented | Optimizing | Pass
RS.RP-1 | Incident Response Plan | Respond | Documented | Optimizing | Pass
RC.BP-1 | Business Continuity Plan | Recover | Documented | Optimizing | Pass
RC.IM-1 | Lessons Learned Documentation | Recover | Not Performed | Optimizing | Fail
RC.RP-1 | Backup and Recovery Plan | Recover | Managed | Optimizing | Pass